## TideUAT
Order | ID | Phase | Gate | Type | User | Feature/Serial | Objective | Benefit | Pass Criteria | Fail Impact | Status | Remarks
1 | TIDE-UAT-001 | Smoke | S1 | Functional | SOC Analyst | Authentication Login | I wish to sign in with my assigned account. | So that I can access my operational workspace. | After entering valid credentials, the user lands on the main workspace. If credentials are invalid, a clear error message is shown on the login page. | Block all further UAT
2 | TIDE-UAT-002 | Smoke | S1 | Functional | SOC Analyst | Authentication Logout | I wish to log out when finished. | So that my session cannot be reused by another person. | After selecting logout, the user returns to the sign-in page and protected pages are no longer accessible without signing in again. | Security sign-off blocked
3 | TIDE-UAT-003 | Smoke | S1 | Functional | Tenant Admin | Active Client Switching | I wish to switch between assigned clients. | So that I can work in the correct tenant context. | After selecting a different client, the page refreshes and visible data updates to that client only. | All tenant-scoped tests become unreliable
4 | TIDE-UAT-004 | Smoke | S1 | Functional | Platform Superadmin | Tenant List Visibility | I wish to see all tenants. | So that I can administer the full platform estate. | A platform superadmin can view the full tenant list, while a tenant admin only sees tenants they are assigned to. | Admin-path test sequencing invalid
5 | TIDE-UAT-009 | Smoke | S1 | Functional | SOC Analyst | Rule Health List | I wish to browse rules with filters and sorting. | So that I can triage detection quality quickly. | Filtering, sorting, and paging update the visible rule list correctly and show consistent totals. | Core SOC workflow blocked
6 | TIDE-UAT-011 | Smoke | S1 | Functional | SOC Analyst | Rule Detail Review | I wish to open full rule details. | So that I can make informed decisions before testing or promotion. | Selecting a rule opens a detail view showing rule content and metadata, and the view can be closed cleanly. | All detail-action checks unreliable
7 | TIDE-UAT-013 | Smoke | S1 | Functional | SOC Analyst | Manual Data Sync | I wish to trigger a sync on demand. | So that I can refresh rule and metrics data when needed. | Starting sync shows progress feedback and, on completion, the rules and metrics on screen refresh to current values. | Rule freshness checks invalid
8 | TIDE-UAT-014 | Smoke | S1 | Functional | SOC Analyst | Promotion Work Queue | I wish to see only promotable staging items. | So that I do not accidentally act on production-only content. | The promotion list shows staging candidates relevant to the active tenant and excludes unrelated environments. | Promotion testing blocked
9 | TIDE-UAT-017 | Smoke | S1 | Functional | SOC Analyst | Threat Actor Filtering | I wish to filter threat actors. | So that I can focus on relevant adversaries. | Search and filter controls update the actor list and counts in a predictable way. | Threat coverage flow blocked
10 | TIDE-UAT-020 | Smoke | S1 | Functional | SOC Analyst | Heatmap Generation | I wish to generate a threat coverage heatmap. | So that I can visually identify detection gaps. | The matrix renders for selected actors and displays clear covered and gap states across techniques. | Gap-analysis flow blocked
11 | TIDE-UAT-023 | Smoke | S1 | Functional | Detection Engineer | Sigma Rule Discovery | I wish to find Sigma rules by technique and category. | So that I can identify candidate detections efficiently. | Applying search and filter criteria narrows the Sigma list and displays relevant results only. | Detection-engineering flow blocked
12 | TIDE-UAT-024 | Smoke | S1 | Functional | Detection Engineer | Sigma Conversion | I wish to convert Sigma content into deployable queries. | So that I can prepare detections for the target SIEM. | A successful conversion displays readable output and a conversion result panel; invalid input returns a clear error. | Deploy path not testable
13 | TIDE-UAT-031 | Smoke | S1 | Functional | SOC Analyst | CVE Overview Dashboard | I wish to review CVE exposure at a glance. | So that I can prioritize mitigation work. | The CVE overview loads with counts and list entries that match the current tenant data. | Inventory risk workflow blocked
14 | TIDE-UAT-037 | Smoke | S1 | Functional | SOC Analyst | Baseline Lifecycle | I wish to create and maintain assurance baselines. | So that threat scenarios can be modeled over time. | Baseline create, import, update, and delete actions reflect immediately in baseline lists and detail views. | Baseline/quest flow blocked
15 | TIDE-UAT-042 | Smoke | S1 | Functional | Integration Engineer | External Client Discovery | I wish to list clients available to my integration key. | So that I query only approved tenant data. | The client discovery endpoint returns only tenants the key owner is entitled to access. | Integration UAT blocked
16 | TIDE-UAT-045 | Smoke | S1 | Non-Functional | Security Architect | Transport Protection | I wish all user traffic protected in transit. | So that credentials and sensitive content are protected. | Users are automatically served over HTTPS and security headers are present in browser responses. | Security gate fail
17 | TIDE-UAT-050 | Smoke | S1 | Non-Functional | Lead Systems Engineer | Runtime Health Stability | I wish services to recover from routine failures. | So that production availability is maintained. | After restart or transient failure, application services return healthy and users can sign in and continue work. | Execution environment unstable
18 | TIDE-UAT-005 | Critical Path | C1 | Functional | Tenant Admin | Tenant-Bound Access Control | I wish access rights to follow the active tenant. | So that no user can act outside authorized boundaries. | A user who has rights in one tenant but not another is denied restricted actions in the unauthorized tenant. | Cross-tenant risk
19 | TIDE-UAT-006 | Critical Path | C1 | Functional | Platform Superadmin | Global SIEM Inventory | I wish to manage SIEM entries centrally. | So that connections are governed consistently. | Superadmin can add, edit, and remove SIEM inventory entries; non-superadmin users cannot access this global inventory area. | Credential governance risk
20 | TIDE-UAT-007 | Critical Path | C1 | Functional | Tenant Admin | Client-to-SIEM Linking | I wish to link a client to SIEM environments. | So that rule sync and promotion follow the intended path. | When a SIEM mapping is saved, it appears immediately in the client configuration list and can be removed or updated later. | Sync/promotion routing risk
21 | TIDE-UAT-008 | Critical Path | C1 | Functional | Tenant Admin | Space Selection Validation | I wish invalid SIEM space inputs to be blocked. | So that misconfiguration does not break downstream workflows. | If an invalid space is entered, the system shows a validation message and does not save the mapping. | Operator misconfiguration risk
22 | TIDE-UAT-010 | Critical Path | C1 | Functional | SOC Analyst | Rule Validation Marking | I wish to mark reviewed rules as validated. | So that review actions are documented. | After validation, the same rule card displays updated validation details and remains in context without losing the current page state. | Audit evidence gap
23 | TIDE-UAT-012 | Critical Path | C1 | Functional | SOC Analyst | Rule Test Run | I wish to test a rule before promotion. | So that I can confirm expected behavior. | Running a test shows a result panel with outcome details. If required context is missing, the user receives a clear actionable message. | Promotion readiness unknown
24 | TIDE-UAT-015 | Critical Path | C1 | Functional | SOC Analyst | Promotion Safety Checks | I wish ambiguous promotions to be blocked. | So that no rule is promoted to the wrong destination. | When routing is ambiguous, promotion is prevented and the user receives a clear explanation of what must be corrected. | Wrong-target promotion risk
25 | TIDE-UAT-016 | Critical Path | C1 | Functional | SOC Analyst | Promotion Completion Feedback | I wish successful promotions to refresh automatically. | So that I can trust what I see after an action. | After a successful promotion, a success notification appears and promotion counts/lists update without manual reload. | Operator trust degradation
26 | TIDE-UAT-018 | Critical Path | C1 | Functional | SOC Analyst | Threat Coverage Accuracy | I wish coverage percentages to reflect current tenant detections. | So that reporting and planning are reliable. | Coverage percentages and covered technique counts align with visible detections for the active tenant. | Decision quality risk
27 | TIDE-UAT-019 | Critical Path | C1 | Functional | SOC Analyst | Threat Intelligence Refresh | I wish to refresh threat intelligence sources. | So that assessments use up-to-date threat data. | After sync, the user sees a completion summary (success, partial, or failed) and updated threat metrics. | Threat posture stale
28 | TIDE-UAT-021 | Critical Path | C1 | Functional | SOC Analyst | Technique Drilldown | I wish to open technique-level detail from the heatmap. | So that I can review available detections for that technique. | Selecting a technique opens a side panel with related information and allows deeper rule review from that panel. | Remediation flow degraded
29 | TIDE-UAT-022 | Critical Path | C1 | Functional | SOC Analyst | Heatmap Export | I wish to export heatmap outputs. | So that I can share evidence with stakeholders. | Export action produces a downloadable report artifact for the selected scope. | Sign-off artifact risk
30 | TIDE-UAT-025 | Critical Path | C1 | Functional | Detection Engineer | Sigma Pre-Validation | I wish to validate Sigma content before converting. | So that I catch issues early. | Validation clearly indicates pass or failure and points out issues when present. | Deployment defects increase
31 | TIDE-UAT-026 | Critical Path | C1 | Functional | Detection Engineer | Sigma Deployment Guardrails | I wish deployments to be restricted to approved client targets. | So that detections cannot be pushed to unauthorized destinations. | Deployment is blocked for unapproved or incomplete target selection and allowed only for valid assigned targets. | Cross-tenant deployment risk
32 | TIDE-UAT-027 | Critical Path | C1 | Functional | Detection Engineer | Sigma Deploy Visibility | I wish newly deployed rules to appear quickly. | So that I can verify deployment outcomes in the platform. | After successful deployment, a confirmation appears and the rule becomes visible in subsequent rule health views. | Operational lag/risk
33 | TIDE-UAT-028 | Critical Path | C1 | Functional | Tenant Admin | System Inventory Management | I wish to create and maintain system records. | So that inventory reflects real operational environments. | Creating, editing, and deleting systems updates the visible system list immediately with correct names and classifications. | Asset model unreliable
34 | TIDE-UAT-029 | Critical Path | C1 | Functional | Tenant Admin | Host Inventory Management | I wish to manage hosts under each system. | So that asset-level risk mapping stays accurate. | Host add, edit, and delete actions are reflected immediately in the host list for the selected system. | Asset mapping unreliable
35 | TIDE-UAT-030 | Critical Path | C1 | Functional | Tenant Admin | Nessus Import | I wish to import scan files. | So that host and software records can be onboarded faster. | A valid upload shows import results and updates inventory views; invalid or empty files display a clear failure reason. | Coverage source incomplete
36 | TIDE-UAT-032 | Critical Path | C1 | Functional | SOC Analyst | CVE to Technique Mapping | I wish to add or remove CVE technique mappings. | So that analysis reflects real-world relevance. | Mapping changes appear immediately in the CVE detail view and persist after refresh. | CVE mapping fidelity risk
37 | TIDE-UAT-033 | Critical Path | C1 | Functional | SOC Analyst | CVE Detection Records | I wish to record detection coverage notes for CVEs. | So that compensating controls are visible to the team. | Adding or removing detection records updates the CVE detection section instantly and keeps entries consistent. | Compensating control tracking gap
38 | TIDE-UAT-034 | Critical Path | C1 | Functional | SOC Analyst | Detection Application by Asset | I wish to apply detections to specific systems or hosts. | So that mitigation status is tracked at asset level. | Applied detection state appears under affected systems/hosts and can be removed with immediate visual update. | Remediation state incorrect
39 | TIDE-UAT-035 | Critical Path | C1 | Functional | Tenant Admin | CISA Feed Update | I wish to ingest and reset KEV data. | So that vulnerability intelligence remains current in air-gapped operations. | Feed import confirms loaded results, and reset returns the platform to baseline catalogue behavior. | Vuln intelligence drift
40 | TIDE-UAT-036 | Critical Path | C1 | Functional | Tenant Admin | Offline Mapping Upload | I wish to upload ATT&CK/CVE mapping files offline. | So that enrichment can be maintained without internet access. | A valid mapping upload confirms success and updates CVE-to-technique enrichment behavior. | Air-gap enrichment risk
41 | TIDE-UAT-038 | Critical Path | C1 | Functional | SOC Analyst | Baseline Snapshots | I wish to capture baseline coverage snapshots. | So that I can preserve point-in-time audit evidence. | Creating a snapshot adds it to audit history, and deleting removes it from the same history list. | Historical evidence gap
42 | TIDE-UAT-039 | Critical Path | C1 | Functional | SOC Analyst | Coverage Quest Workflow | I wish to run guided technique-by-technique coverage tasks. | So that baseline completion is systematic and trackable. | Starting a quest opens the guided flow, progress is visible during completion, and ending/completing returns the user to baseline context. | HITL completion flow broken
43 | TIDE-UAT-040 | Critical Path | C1 | Functional | Tenant Admin | Client User Management | I wish to assign users and roles in my tenant. | So that access aligns with team responsibilities. | User assignment and role updates appear immediately in client user lists and are reflected in permitted actions. | Tenant ops/admin risk
44 | TIDE-UAT-041 | Critical Path | C1 | Functional | Platform Superadmin | Platform-Admin Toggle Safety | I wish to change platform-admin status safely. | So that governance changes do not create accidental lockouts. | Granting/revoking another user works, while unsafe self-change actions are blocked with a clear warning. | Lockout/governance risk
45 | TIDE-UAT-043 | Critical Path | C1 | Functional | Integration Engineer | External Query Safety | I wish external queries to be read-only. | So that integrations cannot alter platform data. | Read-only queries succeed with structured results; mutation attempts are rejected with an explicit error. | Data integrity risk
46 | TIDE-UAT-044 | Critical Path | C1 | Functional | Integration Engineer | External Tenant Boundary | I wish external access to enforce tenant boundaries. | So that integrations cannot cross tenant lines. | Requests for unauthorized tenants are denied and multi-tenant users are prompted to select a tenant when required. | Data leakage risk
47 | TIDE-UAT-047 | Critical Path | C1 | Non-Functional | Security Architect | Tenant Isolation Controls | I wish data to remain isolated by tenant. | So that one tenant cannot view another tenant data. | Changing tenant context changes all visible operational data, and unauthorized cross-tenant attempts are denied. | Critical security failure
48 | TIDE-UAT-048 | Critical Path | C1 | Non-Functional | Security Architect | Least Privilege Enforcement | I wish privileged features limited to proper roles. | So that administrative exposure is minimized. | Platform-only administration areas are inaccessible to non-authorized roles. | Privilege escalation risk
49 | TIDE-UAT-052 | Critical Path | C1 | Non-Functional | Lead Systems Engineer | Graceful Failure Handling | I wish user experience to degrade gracefully during sync issues. | So that operations continue even when dependencies fail. | When upstream sync fails, users see meaningful warnings while key pages remain accessible. | Availability risk
50 | TIDE-UAT-056 | Critical Path | C1 | Functional | Tenant Admin | Per-Tenant Role Templates | I wish role templates configurable per tenant. | So that access policy can differ by client. | Changing role permissions in one tenant does not alter role behavior in another tenant. | Authorization drift risk
51 | TIDE-UAT-057 | Critical Path | C1 | Functional | Detection Engineer | Tenant-Scoped Sigma Assets | I wish Sigma assets assigned per tenant. | So that teams only use approved conversion assets. | After assignment, each tenant sees only its designated pipeline/template assets in Sigma workflows. | Incorrect conversion context
52 | TIDE-UAT-059 | Critical Path | C1 | Functional | SOC Analyst | System and Baseline Move Flow | I wish to move assets with pre-check guidance. | So that migrations are safe and predictable. | Pre-check clearly reports readiness and, after move, source and destination views reflect the new assignment correctly. | Data relocation risk
53 | TIDE-UAT-046 | Full Regression | R1 | Non-Functional | Security Architect | Session Hardening | I wish session handling to reduce hijacking risk. | So that authenticated sessions are safer. | Session behavior follows secure cookie expectations and sessions cannot be reused after logout. | Security finding
54 | TIDE-UAT-049 | Full Regression | R1 | Non-Functional | Lead Systems Engineer | Air-Gapped Readiness | I wish core workflows to function offline. | So that the product is deployable in disconnected environments. | With no outbound internet, core pages and baseline workflows remain usable using bundled/local data. | Deployment readiness risk
55 | TIDE-UAT-051 | Full Regression | R1 | Non-Functional | UI Lead | Responsive In-Page Updates | I wish user actions to update only relevant page areas. | So that operations feel fast and focused. | Common actions update the relevant card/table section without disruptive full-page reload behavior. | UX performance degradation
56 | TIDE-UAT-053 | Full Regression | R1 | Non-Functional | Auditor | Decision Traceability | I wish key analyst decisions to be traceable. | So that audits can validate who decided what and when. | Validation actions and baseline history entries are visible in the UI and remain available for later review. | Audit/readiness risk
57 | TIDE-UAT-054 | Full Regression | R1 | Non-Functional | Lead Systems Engineer | List Scalability | I wish large datasets to remain navigable. | So that usability remains stable as volume grows. | Large lists remain responsive through working pagination/filtering controls with accurate totals. | Performance/scalability risk
58 | TIDE-UAT-055 | Full Regression | R1 | Non-Functional | UI Lead | Deterministic Interaction Behavior | I wish dialog and table actions to behave consistently. | So that users can trust repeated workflows. | The same action sequence produces the same visible result each time, including clear success/failure notifications. | Operator confidence risk
59 | TIDE-UAT-058 | Full Regression | R1 | Non-Functional | Security Architect | Diagnostic Governance | I wish advanced diagnostics tightly controlled. | So that troubleshooting cannot bypass governance. | Only authorized platform users can access diagnostic query tooling, and unsafe operations are not allowed. | Security/governance risk
60 | TIDE-UAT-060 | Full Regression | R1 | Non-Functional | Lead Systems Engineer | Data Persistence | I wish critical data to survive restarts. | So that operational continuity is preserved. | After restarting containers, prior tenant data, validation history, and operational records remain intact. | Operational durability risk

## TideUAT-Prioritised
Order | Phase | Gate | UAT ID | Feature/Serial | Run Rule | Fail Impact
1 | Smoke | S1 | TIDE-UAT-001 | Authentication Login | Verify users can sign in first | Block all further UAT
2 | Smoke | S1 | TIDE-UAT-002 | Authentication Logout | Verify session termination baseline | Security sign-off blocked
3 | Smoke | S1 | TIDE-UAT-003 | Active Client Switching | Verify tenant switching works | All tenant-scoped tests become unreliable
4 | Smoke | S1 | TIDE-UAT-004 | Tenant List Visibility | Verify tenant visibility by role | Admin-path test sequencing invalid
18 | Critical Path | C1 | TIDE-UAT-005 | Tenant-Bound Access Control | Validate tenant-bound authorization | Cross-tenant risk
19 | Critical Path | C1 | TIDE-UAT-006 | SIEM Inventory Governance | Validate platform-only SIEM governance | Credential governance risk
20 | Critical Path | C1 | TIDE-UAT-007 | Client-to-SIEM Linking | Validate client SIEM mapping workflow | Sync/promotion routing risk
21 | Critical Path | C1 | TIDE-UAT-008 | Per-SIEM Space Validation | Validate mapping input guardrails | Operator misconfiguration risk
5 | Smoke | S1 | TIDE-UAT-009 | Rule Health List | Verify primary rules view loads | Core SOC workflow blocked
22 | Critical Path | C1 | TIDE-UAT-010 | Rule Validation Marking | Validate auditable human decision logging | Audit evidence gap
6 | Smoke | S1 | TIDE-UAT-011 | Rule Detail Review | Verify rule detail panel opens | All detail-action checks unreliable
23 | Critical Path | C1 | TIDE-UAT-012 | Rule Test Run | Validate rule test experience | Promotion readiness unknown
7 | Smoke | S1 | TIDE-UAT-013 | Manual Data Sync | Verify manual sync feedback path | Rule freshness checks invalid
8 | Smoke | S1 | TIDE-UAT-014 | Promotion Work Queue | Verify promotion queue loads correctly | Promotion testing blocked
24 | Critical Path | C1 | TIDE-UAT-015 | Promotion Safety Checks | Validate promotion fail-closed logic | Wrong-target promotion risk
25 | Critical Path | C1 | TIDE-UAT-016 | Promotion Completion Feedback | Validate post-promotion state coherence | Operator trust degradation
9 | Smoke | S1 | TIDE-UAT-017 | Threat Landscape Filters | Verify threats page and filter path | Threat coverage flow blocked
26 | Critical Path | C1 | TIDE-UAT-018 | Threat Coverage Accuracy | Validate coverage correctness | Decision quality risk
27 | Critical Path | C1 | TIDE-UAT-019 | Threat Intel Sync | Validate threat source sync behavior | Threat posture stale
10 | Smoke | S1 | TIDE-UAT-020 | Heatmap Generation | Verify heatmap renders for selected actors | Gap-analysis flow blocked
28 | Critical Path | C1 | TIDE-UAT-021 | Heatmap Technique Drilldown | Validate technique-to-rule drill path | Remediation flow degraded
29 | Critical Path | C1 | TIDE-UAT-022 | Heatmap Export | Validate report export for stakeholders | Sign-off artifact risk
11 | Smoke | S1 | TIDE-UAT-023 | Sigma Rule Discovery | Verify Sigma catalog availability | Detection-engineering flow blocked
12 | Smoke | S1 | TIDE-UAT-024 | Sigma Conversion | Verify conversion engine baseline | Deploy path not testable
30 | Critical Path | C1 | TIDE-UAT-025 | Sigma Pre-Validation | Validate rule syntax QA gate | Deployment defects increase
31 | Critical Path | C1 | TIDE-UAT-026 | Sigma Deployment Guardrails | Validate tenant-safe deployment routing | Cross-tenant deployment risk
32 | Critical Path | C1 | TIDE-UAT-027 | Sigma Deploy Visibility | Validate deployment-to-visibility loop | Operational lag/risk
33 | Critical Path | C1 | TIDE-UAT-028 | Systems CRUD | Validate system inventory lifecycle | Asset model unreliable
34 | Critical Path | C1 | TIDE-UAT-029 | Hosts CRUD | Validate host inventory lifecycle | Asset mapping unreliable
35 | Critical Path | C1 | TIDE-UAT-030 | Nessus Import | Validate scan ingest automation | Coverage source incomplete
13 | Smoke | S1 | TIDE-UAT-031 | CVE Overview Dashboard | Verify CVE overview dashboard loads | Inventory risk workflow blocked
36 | Critical Path | C1 | TIDE-UAT-032 | CVE to Technique Mapping | Validate analyst mapping override path | CVE mapping fidelity risk
37 | Critical Path | C1 | TIDE-UAT-033 | CVE Detection Records | Validate CVE detection records | Compensating control tracking gap
38 | Critical Path | C1 | TIDE-UAT-034 | Detection Application by Asset | Validate per-system mitigation application | Remediation state incorrect
39 | Critical Path | C1 | TIDE-UAT-035 | CISA Feed Update | Validate KEV feed ingest/reset lifecycle | Vuln intelligence drift
40 | Critical Path | C1 | TIDE-UAT-036 | Offline Mapping Upload | Validate offline mapping refresh path | Air-gap enrichment risk
14 | Smoke | S1 | TIDE-UAT-037 | Baseline CRUD | Verify baseline module entry path | Baseline/quest flow blocked
41 | Critical Path | C1 | TIDE-UAT-038 | Baseline Coverage Snapshot | Validate audit snapshot creation/deletion | Historical evidence gap
42 | Critical Path | C1 | TIDE-UAT-039 | Coverage Quest Workflow | Validate guided completion workflow | HITL completion flow broken
43 | Critical Path | C1 | TIDE-UAT-040 | Client User Management | Validate user-client-role management | Tenant ops/admin risk
44 | Critical Path | C1 | TIDE-UAT-041 | Platform-Admin Toggle Safety | Validate platform-admin safety controls | Lockout/governance risk
15 | Smoke | S1 | TIDE-UAT-042 | External Client Discovery | Verify integration key can list clients | Integration UAT blocked
45 | Critical Path | C1 | TIDE-UAT-043 | External Query Safety | Validate SQL mutation blocking | Data integrity risk
46 | Critical Path | C1 | TIDE-UAT-044 | External Tenant Boundary | Validate integration tenant boundaries | Data leakage risk
16 | Smoke | S1 | TIDE-UAT-045 | Transport Protection | Verify HTTPS protection baseline | Security gate fail
53 | Full Regression | R1 | TIDE-UAT-046 | Session Hardening | Confirm session hardening behavior | Security finding
47 | Critical Path | C1 | TIDE-UAT-047 | Tenant Isolation Controls | Validate tenant isolation behavior | Critical security failure
48 | Critical Path | C1 | TIDE-UAT-048 | Least Privilege Enforcement | Validate role restriction boundaries | Privilege escalation risk
54 | Full Regression | R1 | TIDE-UAT-049 | Air-Gapped Readiness | Confirm offline operational behavior | Deployment readiness risk
17 | Smoke | S1 | TIDE-UAT-050 | Container Health Resilience | Verify runtime service health gate | Execution environment unstable
55 | Full Regression | R1 | TIDE-UAT-051 | Responsive In-Page Updates | Confirm focused in-page update behavior | UX performance degradation
49 | Critical Path | C1 | TIDE-UAT-052 | Sync Fault Tolerance | Validate graceful degradation under sync faults | Availability risk
56 | Full Regression | R1 | TIDE-UAT-053 | Decision Traceability | Confirm traceability completeness | Audit/readiness risk
57 | Full Regression | R1 | TIDE-UAT-054 | List Scalability | Confirm bounded list behavior under load | Performance/scalability risk
58 | Full Regression | R1 | TIDE-UAT-055 | Deterministic Interaction Behavior | Confirm deterministic state transitions | Operator confidence risk
50 | Critical Path | C1 | TIDE-UAT-056 | Per-Tenant Role Templates | Validate per-tenant permission templates | Authorization drift risk
51 | Critical Path | C1 | TIDE-UAT-057 | Tenant-Scoped Sigma Assets | Validate tenant-scoped sigma assets | Incorrect conversion context
59 | Full Regression | R1 | TIDE-UAT-058 | Diagnostic Governance | Confirm superadmin-only diagnostics and read-only behavior | Security/governance risk
52 | Critical Path | C1 | TIDE-UAT-059 | System and Baseline Move Flow | Validate preflight and move consistency | Data relocation risk
60 | Full Regression | R1 | TIDE-UAT-060 | Data Persistence | Confirm restart persistence on mounted data | Operational durability risk